## Sheet1
Chapter 1234 Flight Plan |  |  |  |  | 2021-2025
Chapter 1234's Mission -
Support the mission, vision, goals and objectives of EAA. Create an environment to nuture growth of recreational aviation in our community, focus on flight safety, education, aircraft building, maintenance and innovation
1 | Chapter Marketing
Item | Objective | Tasks | Goals | Timeline | (PIC/SIC)
1.1 | Increase Chapter awareness at our airport | Utilize customized chapter promo materials (rack cards, fliers, business cards) around the airport. Write personal letters to each of the hangar renters/owners on the airfield about the new EAA Chapter and its benefits | Increase membership by 4 members per year for 5 years | Complete by June 2021 | John and Mollee
1.2 | Increase Chapter visbility in our region | Advertise chapter events (fly-ins, open house, gatherings, etc.) via ChapterBlast, Social Flight, and EAA Calendar of Events. Write articles for local Newspaper and Radio. Invite local media to chapter events. | Create Chapter awareness off airport - grow membership | Begin May 2021 - Continue Yearly | Megan/Bob
1.3 | Create visibility within city admin | Attend City Airport Advisory meetings & city council meetings. Retro-active: Invite city officials to chapter events at the airport. | Create visibility and value at city mgmt level | All city airport meetings and retro-active at chapter events | Charlie/Jane
2 | Chapter Activites
Item | Objective | Tasks | Goals | Timeline | (PIC/SIC)
2.1 | Host Chapter Burger Burn/Open House Fly-In | Organize first chapter fly-in and burger burn. Charge $5 per plate. Serve burgers, hot dogs, chips, and soda. | Raise Money, grow awareness, gain 1-2 members | May, September Events - ensure yearly calendar consistancy | Serena/Steve
2.2 | Host bi-annual Young Eagle Rallies | Using resources provided by EAA Chapter and Young Eagles office, organize two Young Eagles rallies each year. (May and Sept.) | Introduce kids ages 8-17 to the basics of airplanes, airports and careers | On International Young Eagles Day June 12 2021 and August - yearly consistancy | Chris/Jim
2.3 | Host an EAA Build and Fly or YE Workshop for youth - parents ae welcome too! | Using resources provided by the EAA Chapter's office, organize a turn key youth program (May and Sept.) | Bring kids back to the chapter after a Young Eagles event | Three weeks after a young Eagles Event. Start small, expand yearly | Chris/Mark
3 | Airplane Building & Maintenance
Item | Objective | Tasks | Goals | Timeline | (PIC/SIC)
3.1 | Encourage building at the chapter level | Host a "Building Buffet" Workhop - riveting, wood rib making, welding mini seminars | Demonstrate basic building concepts to area members | September this year - expand or refine yearly - make it a "go to" event | Mark/Joe
3.2 | Encourage building at the chapter level | Solicit work bench, tool and equipment & donations for Chapter 1234's "Builders Corner" - always ask for "builders' updates" at monthly Mmeber gathering meeting to establish a norm. | Provide tools to chapter members who don't have access to them | Start this October and committ o a monthly routine | Joe/Mark
4 | Flight Safety
Item | Objective | Tasks | Goals | Timeline | (PIC/SIC)
4.1 | Establish a VMC/IMC Club | Set up an IMC and VMC Club. Host one meeting each month, alternating between VMC and IMC programming. Craete a welcoming enviroment to chapter activities. | Encourage safe flying and gain new chapter members | Survey Members now - Committ to forming IMC/VMC by next year | Radek/John
4.2 | Host an FAA Faast Seminar | Host FAA FAASTeam twice a year | Encourage members to take part in the FAA Wings Program | Contact FAA February 2021 - yearly programming | Radek/John
5 | Chapter Fundraising
Item | Objective | Tasks | Goals | Timeline | (PIC/SIC)
5.1 | Raise money to purchse chapter clubhouse | Host 4 Pancake Breakfast/year. (April, June, August, Oct.) Always advertise the reason for your fundraising. | Avg 120 attendees @ $3 net profit of $360/event or $1440/year | Fundraising planning starts ASAP and continues Yearly for Great Results. | Kristi/Kevin
5.2 | Raise money to purchase chapter clubhouse | Host EAA Tri-Motor during the summer of 2018 | Raise $2000.00 | Contact EAA Air-Tours department by June 2021 | Mike/Kristi